## Project Timeline
SORTING VISUALISER PROJECT TIMELINE
AT RISK | TASK NAME | DESCRIPTION | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION
| Task 1 - Research project ideas | Research project ideas, with focus on project viability and scope | Complete | Kevin | 2020-09-08 | 2020-09-25 | 17
| Task 2 - Research technologies | Research technologies that can be used to develop the project | Complete | Kevin | 2020-09-26 | 2020-10-16 | 20
| Task 3 - Decide on system design | Decide on the system design, how each component will | Complete | Kevin | 2020-10-17 | 2020-10-24 | 7
| Task 4 - Decide on feature timeline | Decide on what features will be developed first | Complete | Kevin | 2020-10-25 | 2020-11-01 | 5
| Task 5 - Implement project | Work on project begins | Complete | Kevin | 2020-11-02 | 2020-04-24 | 180
| Subtask 1 - Get basic visualisation working | Get basic visualisation working - implement a default sorting algorithm and visualise it | Complete | Kevin | 2020-11-03 | 2020-11-11 | 8
| Subtask 2 - Start user authentication | Start on user authentication, which allows a user to register and sign in to an account | Complete | Kevin | 2020-11-12 | 2020-11-20 | 8
| Task 6 - PROJECT ON HOLD | Project on hold for Christmas/Work on other projects | Complete | Kevin | 2020-11-21 | 2020-12-28 | 37
| Subtask 3 - Finish user authentication | Finish user authentication | Complete | Kevin | 2020-12-29 | 2020-01-10 | 12
| Subtask 4 - Host Flask server on PythonAnywhere | Set up Flask server on PythonAnywhere | Complete | Kevin | 2020-01-11 | 2020-01-12 | 1
| Subtask 5 - Enhance visualization | Enhance visualisation - add more sorting algorithms, fix bugs, etc. | Complete | Kevin | 2020-01-13 | 2020-02-13 | 14
| Subtask 6 - Implement uploading of past sorts | Implement uploading of past sorts to database | Complete | Kevin | 2020-02-13 | 2020-02-21 | 8
| Task 7 - Wire everything together, bug fix, and test | Wire everything up - push to GitHub | Complete | Kevin | 2020-02-22 | 2020-03-31 | 38
| Task 8 - Work on dissertation | Dissertation work | Complete | Kevin | 2020-12-29 | 2020-04-24 | 117

## Project Timeline - BLANK
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.