## Project Timeline
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Task 1 - Research project ideas |  | Complete | Kevin | 2020-09-08 | 2020-09-20 | 12
| Task 2 - Research technologies |  | Complete | Kevin | 2020-09-21 | 2020-10-11 | 20
| Task 3 - Decide on system design |  | Complete | Kevin | 2020-10-12 | 2020-10-20 | 8
| Task 4 - Decide on feature timeline |  | Complete | Kevin | 2020-10-21 | 2020-10-26 | 5
| Task 5 - Implement project |  | Complete | Kevin | 2020-10-27 | 2020-04-24 | 180
| Subtask 1 - Get basic visualization working |  | Complete | Kevin | 2020-10-28 | 2020-11-07 | 10
| Subtask 2 - Start user authentication |  | Complete | Kevin | 2020-11-08 | 2020-11-15 | 7
| Task 6 - PROJECT ON HOLD |  | Complete | Kevin | 2020-11-16 | 2020-12-20 | 34
| Subtask 3 - Finish user authentication |  | Complete | Kevin | 2020-12-21 | 2020-12-29 | 8
| Subtask 4 - Host Flask server on PythonAnywhere |  | Complete | Kevin | 2020-12-30 | 2020-12-30 | 0
| Subtask 5 - Enhance visualization |  | Complete | Kevin | 2020-12-31 | 2020-01-14 | 14
| Subtask 6 - |  | Complete |  | 2020-04-24 | 2020-04-24 | 0
| Task 7 - Work on dissertation |  | Complete | Kevin | 2020-01-15 | 2020-02-02 | 18
CLICK HERE TO CREATE IN SMARTSHEET

## Project Timeline - BLANK
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.